## Weekly Deliverables
Week | Task | Deliverable | Estimated Time (hrs)
Week 1 | Environment Setup | Azure Cloud Shell ready | 2
Week 1 | Clone Repo | GitHub repo cloned | 1
Week 1 | Run Flask App | Local Flask app running | 3
Week 2 | Implement Makefile | make all passes | 3
Week 2 | Local Prediction Test | Prediction JSON returned | 2
Week 2 | Azure App Service Setup | Web App deployed | 4
Week 3 | CI/CD Pipeline | Azure Pipeline successful | 5
Week 3 | Azure Deployment Test | HTTPS prediction works | 3
Week 3 | Logging & Monitoring | Logs streamed successfully | 2
Week 4 | Documentation | README completed | 3
Week 4 | Demo Video | Screencast recorded | 2

## Quarterly Plan
Quarter | Focus Area | Deliverables
Q1 | Azure Fundamentals | Cloud Shell, App Service, Resource Groups
Q1 | Python Microservices | Flask API, unit tests
Q2 | CI/CD | Azure Pipelines, GitHub integration
Q2 | Monitoring & Logging | App Service logs, diagnostics
Q3 | Infrastructure as Code | Terraform, Packer
Q4 | Capstone & Optimization | Final project and portfolio review

## Yearly Plan
Timeframe | Project Phase | Description
Q1 | Initial MVP Deployment | Deploy Flask ML microservice to Azure App Service with CI/CD
Q2 | Reliability Improvements | Improve test coverage, error handling, and input validation
Q3 | Monitoring & Observability | Add structured logging, Azure Application Insights, and alerts
Q4 | Scalability & Automation | Add autoscaling, containerization, and infrastructure as code